## Summary
PDFVault — Development Work Log
Prepared for Client Review ¦ Report Date: 21 July 2026
Project Start | Report Date | Active Weeks | Total Changes Shipped | Frontend Changes | Backend Changes
19 April 2026 | 21 July 2026 | ~13 Weeks | 410 | 310 | 100
Monthly Activity Breakdown
Month | Frontend Changes | Backend Changes | Total Changes | FE % | BE %
April 2026 | 30 | 5 | 35 | 85.71% | 14.29%
May 2026 | 33 | 3 | 36 | 91.67% | 8.333%
June 2026 | 67 | 19 | 86 | 77.91% | 22.09%
July 2026 | 180 | 73 | 253 | 71.15% | 28.85%
TOTAL | 310 | 100 | 410

## By Category
Changes Grouped by Category
Category | Total Changes | % of All Changes
Editor | 101 | 24.63%
DevOps / Infra | 81 | 19.76%
UI / UX | 68 | 16.59%
Payments & Subscriptions | 50 | 12.2%
Auth | 39 | 9.512%
File Handling | 24 | 5.854%
Internationalisation | 14 | 3.415%
Dashboard | 14 | 3.415%
Testing | 10 | 2.439%
File Conversion | 9 | 2.195%
TOTAL | 410 | 100%

## Change Logs
PDFVault — Full Development Change Log
Date | Area | Description | Category
2026-07-21 | Frontend | Added a retry option after a card decline and made sure subscription checks are confirmed before showing the paywall. | Payments & Subscriptions
2026-07-21 | Frontend | Fixed signature centering, toolbar overflow, and improved the layout on convert pages. | UI / UX
2026-07-21 | Frontend | Fixed the home navigation, added a document picker to tool tiles, and made the language dropdown open upward on the dashboard. | UI / UX
2026-07-21 | Frontend | Fixed the composer so it clears the previous PDF when a user picks a different tool. | Editor
2026-07-21 | Frontend | Confirmed subscription status on the server and stopped an unwanted resync after a user cancels. | Payments & Subscriptions
2026-07-21 | Frontend | Improved the translation service so it loads more efficiently and remembers each user's chosen language. | Internationalisation
2026-07-21 | Frontend | Improved the translation service by saving language choice in the browser and rescanning pages for new content. | Internationalisation
2026-07-21 | Frontend | Aligned the file conversion flow with the client's spec and added a testing harness for user acceptance. | File Conversion
2026-07-21 | Frontend | Added extra diagnostic logging to help track down issues in various components. | DevOps / Infra
2026-07-21 | Frontend | Added the ability to remember a user's chosen language between visits. | Internationalisation
2026-07-20 | Frontend | Removed the Apple sign-in option, tidied the language menu, and added sign-in and paywall checks to the compress tool. | Auth
2026-07-20 | Frontend | Added a helper that keeps the translated page in sync when users navigate between routes. | Internationalisation
2026-07-20 | Frontend | Replaced the landing page hero illustration with a nicer image. | UI / UX
2026-07-20 | Frontend | Added the ability to automatically resume a file upload after a user signs in, with better handling of files waiting to be processed. | File Handling
2026-07-20 | Frontend | Updated the default theme settings and added a light/dark theme toggle. | UI / UX
2026-07-20 | Frontend | Added dark-mode styling to the landing page and made the theme toggle more visible. | UI / UX
2026-07-20 | Frontend | Added a file preview inside the paywall popup so users can see what they're about to unlock. | Payments & Subscriptions
2026-07-20 | Frontend | Made sure users are signed in and subscribed before exporting or extracting images. | Auth
2026-07-19 | Frontend | Made every signed-out prompt in the editor use the same sign-in popup for consistency. | Auth
2026-07-19 | Frontend | Added a diagnostic trace file to help investigate PDF exports on rotated pages in Chromium. | DevOps / Infra
2026-07-18 | Frontend | Added an automated end-to-end test for the signed-out export sign-in flow. | Testing
2026-07-18 | Frontend | Fixed the paywall so signed-out users are sent to sign in first, with a clear escape route if something goes wrong. | Auth
2026-07-18 | Frontend | Fixed the paywall popup so it no longer appears transparent. | UI / UX
2026-07-18 | Frontend | Fixed a race condition that could cancel a successful payment right after it went through. | Payments & Subscriptions
2026-07-18 | Frontend | Fixed the language switcher so it shows every available language, not just English and Spanish. | Internationalisation
2026-07-18 | Frontend | Disabled the translation service's default floating language switcher so only our custom one is visible. | Internationalisation
2026-07-18 | Frontend | Added a CSS-based fallback to hide the translation service's floating switcher when its own setting is ignored. | Internationalisation
2026-07-18 | Frontend | Fixed export so signed-out users are asked to sign in before hitting the paywall. | Auth
2026-07-18 | Frontend | Made the paywall show up before heavy processing starts, and made cancelling stop it cleanly. | Payments & Subscriptions
2026-07-18 | Frontend | Fixed export so it waits for the sign-in check to complete before running. | Auth
2026-07-18 | Frontend | Removed a brief flash of the drop zone and added a proper confirm dialog for sign-in prompts. | UI / UX
2026-07-18 | Frontend | Made the All Tools popup close after picking a tile, plus a small batch of editor polish fixes. | UI / UX
2026-07-18 | Frontend | Fixed post-signin restore so files are saved first, then opened, with a loader shown while it happens. | File Handling
2026-07-18 | Frontend | Made uploaded files open through the composer with the correct saved document link. | File Handling
2026-07-18 | Frontend | Added a loading skeleton and a bottom-left upload progress indicator during post-signin restore. | UI / UX
2026-07-18 | Frontend | Fixed an issue where the URL was being changed mid-flow during auto-launch, which could break navigation. | UI / UX
2026-07-18 | Frontend | Stopped sending users back to the dashboard when a document fails to load but they still have a local file open. | Editor
2026-07-18 | Frontend | Made the convert flow save signed-in users' files to My PDFs before opening the editor. | File Handling
2026-07-18 | Frontend | Added a sign-in requirement to the convert pages for signed-out users. | Auth
2026-07-18 | Frontend | Fixed a build issue by reverting the All Tools catalog to a server component and closing the modal on route change. | DevOps / Infra
2026-07-18 | Frontend | Fixed a build issue by marking the All Tools catalog as a client component so its callbacks work. | DevOps / Infra
2026-07-18 | Frontend | Rebuilt the paywall popup as a clean three-step flow matching the payment design mockup. | Payments & Subscriptions
2026-07-18 | Frontend | Added multi-language SEO tags and expanded the list of translated languages. | Internationalisation
2026-07-18 | Frontend | Added an animated loader and an apologetic message on the editor loading screen. | UI / UX
2026-07-18 | Frontend | Added bulk delete, a duplicate-name check, the language switcher on all dashboard screens, and improved the document authentication flow. | Dashboard
2026-07-18 | Backend | Adjusted internal configuration so the translation service key is recognised. | Internationalisation
2026-07-17 | Frontend | Ran a production-readiness audit and shipped critical fixes plus polish improvements. | DevOps / Infra
2026-07-17 | Frontend | Made every tool tile route through the composer and automatically open the matching dialog. | UI / UX
2026-07-17 | Frontend | Added support for two-factor sign-in with email, phone, and authenticator app codes. | Auth
2026-07-17 | Frontend | Re-styled the paywall popup with our design tokens and added a data retention notice. | Payments & Subscriptions
2026-07-17 | Frontend | Restyled the cancellation flow to match the paywall design and added a retention notice. | Payments & Subscriptions
2026-07-16 | Frontend | Centered the All Tools popup in the viewport. | UI / UX
2026-07-16 | Frontend | Switched to a full-page navigation after sign-in so the session sticks on mobile Safari. | Auth
2026-07-16 | Frontend | Added pending file storage and hydration so users pick up right where they left off after signing in. | File Handling
2026-07-16 | Frontend | Opened All Tools in a modal and made the landing page auto-save the uploaded file after sign-in. | UI / UX
2026-07-16 | Frontend | Removed landing page tiles for tools we don't currently offer. | UI / UX
2026-07-16 | Backend | Fixed a strict-typing issue in the billing order-count callback so it compiles cleanly. | Payments & Subscriptions
2026-07-16 | Backend | Finalised the Solidgate payment integration and added a contact form endpoint. | Payments & Subscriptions
2026-07-15 | Frontend | Cleaned up error handling for better readability. | DevOps / Infra
2026-07-15 | Frontend | Updated the footer contact email to support@pdfvault.ai. | UI / UX
2026-07-15 | Frontend | Fixed the dashboard sidebar logo and expanded how notification toasts are stacked. | Dashboard
2026-07-15 | Frontend | Made the subscription page refresh immediately after closing a subscription so the UI updates instantly. | Payments & Subscriptions
2026-07-15 | Frontend | Added new About Us, FAQs, Onboarding Flow, Subscription Terms, and Refund Policy pages. | UI / UX
2026-07-15 | Frontend | Improved the billing settings experience with a warning modal and removed payment-processor branding. | Payments & Subscriptions
2026-07-15 | Frontend | Made the Billing page auto-sync the full payment history on load, plus a manual sync button. | Payments & Subscriptions
2026-07-15 | Frontend | Added a Reset Subscription button so users can self-serve out of stuck states. | Payments & Subscriptions
2026-07-15 | Frontend | Removed old legacy logo and favicon assets in favour of the PDFVault brand marks. | UI / UX
2026-07-15 | Backend | Fixed billing so it uses the correct Solidgate URLs when listing or fetching subscriptions. | Payments & Subscriptions
2026-07-15 | Backend | Stored the cancellation timestamp automatically on cancel so users don't have to manually refresh. | Payments & Subscriptions
2026-07-15 | Backend | Made the billing history show every payment attempt, not just approved ones. | Payments & Subscriptions
2026-07-15 | Backend | Preserved billing history on hard cancellations and cleaned up phantom subscription records. | Payments & Subscriptions
2026-07-15 | Backend | Fixed the parsing of Solidgate's subscription-list response, which returns data as a keyed map. | Payments & Subscriptions
2026-07-15 | Backend | Fixed invoices getting stuck as pending and hid those pending invoices from the invoice list. | Payments & Subscriptions
2026-07-15 | Backend | Made cancel and restore call the correct Solidgate endpoints with valid response codes. | Payments & Subscriptions
2026-07-15 | Backend | Added full self-serve subscription management for users. | Payments & Subscriptions
2026-07-15 | Backend | Added deep history sync from Solidgate exposed via a new endpoint. | Payments & Subscriptions
2026-07-15 | Backend | Added verbose logging on Solidgate REST calls and the history sync for easier debugging. | DevOps / Infra
2026-07-15 | Backend | Added logging of the raw Solidgate subscription response and normalised invoice shapes. | DevOps / Infra
2026-07-14 | Frontend | Fixed footer legal links, sign-up copy, favicon, Google logo, and dark-mode variants. | UI / UX
2026-07-14 | Frontend | Showed the restore-subscription confirmation message and handled the closed subscription state better. | Payments & Subscriptions
2026-07-14 | Frontend | Made the top header show a Dashboard button when the user is signed in. | Dashboard
2026-07-14 | Backend | Kept pre-v3 database driver behaviour when SSL mode is set to required. | DevOps / Infra
2026-07-14 | Backend | Composed the database connection string from AWS Secrets Manager pieces. | DevOps / Infra
2026-07-14 | Backend | Made restore clean up phantom subscription rows when Solidgate returns a not-found error. | Payments & Subscriptions
2026-07-14 | Backend | Made cancel and restore gracefully handle Solidgate's not-found responses. | Payments & Subscriptions
2026-07-13 | Frontend | Updated the paywall layout with new columns and better error and loading states. | Payments & Subscriptions
2026-07-13 | Frontend | Added end-to-end tests for the billing and paywall functionality. | Testing
2026-07-13 | Backend | Added subscription sync from Solidgate and handling for identity rebinding. | Payments & Subscriptions
2026-07-13 | Backend | Improved handling of Solidgate webhook payloads and subscription processing. | Payments & Subscriptions
2026-07-12 | Frontend | Prettified the empty-state markup for the invoices table. | UI / UX
2026-07-12 | Frontend | Simplified the cancellation flow to a two-step feedback and confirm. | Payments & Subscriptions
2026-07-12 | Frontend | Added a global paywall gate at the network layer, both before and after each request. | Payments & Subscriptions
2026-07-12 | Frontend | Added the invoice history table to the billing page. | Payments & Subscriptions
2026-07-12 | Frontend | Added the cancellation and downsell popup to the billing page. | Payments & Subscriptions
2026-07-12 | Frontend | Added the billing settings tab to the dashboard. | Dashboard
2026-07-12 | Frontend | Added the paywall popup and the subscription entitlement hook. | Payments & Subscriptions
2026-07-12 | Frontend | Updated the subscription documentation to reflect our single trial-to-monthly plan. | Payments & Subscriptions
2026-07-12 | Frontend | Added a user-journey walkthrough to the subscription documentation. | Payments & Subscriptions
2026-07-12 | Backend | Added unit tests covering webhook signature verification and idempotency. | Testing
2026-07-12 | Backend | Removed the standalone annual plan from the catalog. | Payments & Subscriptions
2026-07-12 | Backend | Removed the downsell tiers from the cancellation flow. | Payments & Subscriptions
2026-07-12 | Backend | Added the invoice endpoint. | Payments & Subscriptions
2026-07-12 | Backend | Added the lifecycle email pipeline via Amazon SES. | DevOps / Infra
2026-07-12 | Backend | Added the cancellation feedback and downsell endpoints. | Payments & Subscriptions
2026-07-12 | Backend | Added the cancel and restore subscription endpoints. | Payments & Subscriptions
2026-07-12 | Backend | Added the webhook receiver and the reconciliation queue. | Payments & Subscriptions
2026-07-12 | Backend | Added the checkout intent and entitlement endpoints. | Payments & Subscriptions
2026-07-12 | Backend | Set up the initial billing module skeleton, database schema, and configuration. | Payments & Subscriptions
2026-07-12 | Backend | Added subscription discovery notes and an integration plan document. | Payments & Subscriptions
2026-07-11 | Frontend | Renamed the PDF Editor to PDF Composer everywhere, updating all related routes and links. | UI / UX
2026-07-10 | Frontend | Forced a fresh deployment of the frontend service. | DevOps / Infra
2026-07-10 | Frontend | Removed an invalid button style that was breaking the thumbnail sidebar. | UI / UX
2026-07-10 | Frontend | Fixed a type issue when converting saved PDF bytes into a downloadable file. | File Handling
2026-07-10 | Frontend | Added a password show/hide toggle and strength meter, and improved button styles. | Auth
2026-07-10 | Frontend | Triggered a redeploy after updating cloud permissions. | DevOps / Infra
2026-07-10 | Frontend | Made the frontend build fetch secrets from AWS Secrets Manager and added a local build script. | DevOps / Infra
2026-07-10 | Frontend | Added an automatic secret scan on every push and pull request. | DevOps / Infra
2026-07-10 | Frontend | Removed unused image assets from the landing page. | UI / UX
2026-07-10 | Frontend | Refactored the PDF editor tests for better reliability and coverage. | Testing
2026-07-10 | Backend | Made AWS credentials optional so the container's own role can be used automatically. | DevOps / Infra
2026-07-10 | Backend | Added a health-check endpoint and a five-minute grace period for the container health checks. | DevOps / Infra
2026-07-10 | Backend | Improved Clerk webhook handling with raw-body support for signature verification. | Auth
2026-07-10 | Backend | Fixed the deployment workflow to use the correct backend service name. | DevOps / Infra
2026-07-10 | Backend | Made the deployment workflow auto-discover the backend service name. | DevOps / Infra
2026-07-10 | Backend | Added an automatic secret scan on every push and pull request. | DevOps / Infra
2026-07-10 | Backend | Added an automatic deployment workflow for the backend. | DevOps / Infra
2026-07-10 | Backend | Added debug logging around Clerk auth and webhook user creation. | Auth
2026-07-09 | Frontend | Refactored code structure for readability and maintainability. | DevOps / Infra
2026-07-08 | Frontend | Updated branding from PDFedits.io to pdfvault.ai across the app. | UI / UX
2026-07-08 | Frontend | Renamed authentication routes for consistency. | Auth
2026-07-08 | Frontend | Adjusted the landing header height and updated the logo link. | UI / UX
2026-07-08 | Frontend | Updated authentication routes for consistency. | Auth
2026-07-08 | Frontend | Added better logging for Google Drive picker actions and visibility. | DevOps / Infra
2026-07-08 | Frontend | Improved error handling and logging for the Google Drive picker startup. | DevOps / Infra
2026-07-08 | Frontend | Added an Open action to the file table so users can jump into the editor from the dashboard. | Dashboard
2026-07-08 | Frontend | Added a pixel-accurate sign-up screen with Google sign-up support. | Auth
2026-07-08 | Frontend | Added new dashboard illustrations for the Sign & Watermark and Word to PDF tools. | Dashboard
2026-07-08 | Frontend | Added dashboard styles and design tokens for the PDFVault look. | Dashboard
2026-07-08 | Frontend | Added the sidebar navigation design asset from Figma. | UI / UX
2026-07-07 | Frontend | Improved how we detect when the sign-in popup closes and removed a polling workaround. | Auth
2026-07-07 | Frontend | Updated the Google sign-in scope so users can pick files from Drive. | Auth
2026-07-07 | Frontend | Fixed the sign-in page so the form starts below the top menu bar. | Auth
2026-07-07 | Frontend | Added a drag-and-drop file upload zone and improved the offline banner. | File Handling
2026-07-07 | Frontend | Added cloud upload options alongside the existing device upload. | File Handling
2026-07-07 | Frontend | Added debug logging for the Google Drive picker and sign-in events. | DevOps / Infra
2026-07-07 | Frontend | Added the Google Cloud project number needed for Drive Picker file access. | DevOps / Infra
2026-07-07 | Frontend | Wired the Login with Google button on the sign-in page into the Clerk flow. | Auth
2026-07-06 | Frontend | Updated all tool links to use the PDF editor route for consistency. | UI / UX
2026-07-06 | Frontend | Added file conversion functionality and related UI. | File Conversion
2026-07-06 | Frontend | Added Terms and Conditions and improved the legal sections. | UI / UX
2026-07-06 | Frontend | Added the All Tools page and the policy pages under the landing shell. | UI / UX
2026-07-06 | Frontend | Added a pixel-accurate sign-in screen. | Auth
2026-07-05 | Frontend | Skipped loading the translation service on the landing page when the API key is missing. | Internationalisation
2026-07-05 | Frontend | Guarded against the translation service being missing when the language switcher loads. | Internationalisation
2026-07-05 | Frontend | Added a sticky header, animated tabs and cards, and a refined footer to the landing page. | UI / UX
2026-07-05 | Frontend | Promoted the new PDFVault landing page to the site's home page. | UI / UX
2026-07-05 | Frontend | Triggered a Railway rebuild. | DevOps / Infra
2026-07-05 | Frontend | Pinned the Railway start command to our standalone server. | DevOps / Infra
2026-07-05 | Frontend | Added a production start script mirroring the Docker command. | DevOps / Infra
2026-07-03 | Frontend | Updated branding from PDFedits.io to PDFVault across the app. | UI / UX
2026-07-03 | Frontend | Fixed the deployment workflow to use the correct frontend service name. | DevOps / Infra
2026-07-03 | Frontend | Fixed the deployment workflow to use the correct frontend service name. | DevOps / Infra
2026-07-03 | Frontend | Added a GitHub Actions workflow for deploying the frontend automatically. | DevOps / Infra
2026-07-03 | Frontend | Added a GitHub Actions workflow for deploying the frontend automatically. | DevOps / Infra
2026-07-03 | Frontend | Added a GitHub Actions workflow for deploying the frontend automatically. | DevOps / Infra
2026-07-03 | Frontend | Scaffolded the subscription surface for Chargebee and Adyen. | Payments & Subscriptions
2026-07-03 | Frontend | Routed subscription checks, checkout, and portal through the backend API. | Payments & Subscriptions
2026-07-03 | Frontend | Added an Adyen webhook endpoint with signature verification. | Payments & Subscriptions
2026-07-03 | Backend | Improved webhook handling by using the raw request body for signature verification. | Payments & Subscriptions
2026-07-03 | Backend | Added the subscription and Adyen/Chargebee webhook infrastructure. | Payments & Subscriptions
2026-07-03 | Backend | Enabled automatic backend deployment on every push to main. | DevOps / Infra
2026-07-02 | Frontend | Set the icon-only PNG as the new landing page favicon. | UI / UX
2026-07-01 | Frontend | Fixed the landing page upload section to match the design. | UI / UX
2026-07-01 | Frontend | Updated the footer to use the real vault-contour artwork with a measured grid. | UI / UX
2026-07-01 | Frontend | Added a language switcher to the new landing page. | Internationalisation
2026-06-30 | Frontend | Applied consistent formatting across the landing page sections. | UI / UX
2026-06-30 | Frontend | Added extra breathing space to the hero, upload box, and steps section. | UI / UX
2026-06-30 | Frontend | Restored the footer chevron pattern from the original design. | UI / UX
2026-06-30 | Frontend | Updated the footer to use the correct motif from the design art. | UI / UX
2026-06-30 | Frontend | Traced the banner tile layout from the reference art for pixel accuracy. | UI / UX
2026-06-30 | Frontend | Rebuilt the banner gradient and tile pattern to match the design. | UI / UX
2026-06-30 | Frontend | Simplified the footer background to a single centred circle. | UI / UX
2026-06-30 | Frontend | Fixed the footer colour and added a ribbon texture. | UI / UX
2026-06-30 | Frontend | Added Docker support with a Dockerfile and ignore file. | DevOps / Infra
2026-06-30 | Frontend | Wired the landing page header buttons to the Clerk sign-in and sign-up routes. | Auth
2026-06-30 | Frontend | Added a new PDFVault landing page with header, hero, upload area, and steps. | UI / UX
2026-06-30 | Frontend | Updated the hero background to use the real inverted grid asset. | UI / UX
2026-06-30 | Frontend | Added a scrolling testimonials section to the landing page. | UI / UX
2026-06-30 | Frontend | Added a red conversion banner section to the landing page. | UI / UX
2026-06-30 | Frontend | Added a deep-maroon footer section to the landing page. | UI / UX
2026-06-30 | Frontend | Added the PDF tools catalog section to the landing page. | UI / UX
2026-06-30 | Frontend | Removed a large unused reference image from the public folder. | DevOps / Infra
2026-06-30 | Backend | Improved how AWS storage credentials are handled for different deployment environments. | DevOps / Infra
2026-06-30 | Backend | Added a dedicated health-check endpoint for our AWS load balancer and containers. | DevOps / Infra
2026-06-29 | Backend | Added unit tests covering database error filtering, cancellation handling, response formatting, and retry logic. | Testing
2026-06-29 | Backend | Added an audit-events database migration with foreign keys and enums. | DevOps / Infra
2026-06-29 | Backend | Added additional allowed origins for cross-site access. | DevOps / Infra
2026-06-26 | Frontend | Addressed pull request review comments on the translation service integration. | Internationalisation
2026-06-25 | Frontend | Added Weglot-powered Spanish translation with a language switcher. | Internationalisation
2026-06-24 | Frontend | Fixed miscellaneous editor issues. | Editor
2026-06-24 | Frontend | Added comprehensive tests for PDF editor features and edge cases. | Testing
2026-06-24 | Backend | Fixed a cross-site access issue. | DevOps / Infra
2026-06-23 | Backend | Added a one-time staging cleanup script for PDF assets. | DevOps / Infra
2026-06-23 | Backend | Added staging environment setup. | DevOps / Infra
2026-06-22 | Frontend | Added a Split PDF tool with page-range and chunk-splitting options. | Editor
2026-06-22 | Frontend | Added the Split PDF popup for splitting documents into multiple files. | Editor
2026-06-22 | Frontend | Added offline support with local browser storage caching. | File Handling
2026-06-22 | Frontend | Added a locking mechanism for critical file paths with user prompts. | File Handling
2026-06-19 | Frontend | Refactored text editing and export functionality in the editor. | Editor
2026-06-19 | Frontend | Improved page-number overlay handling and optimised the save process. | Editor
2026-06-19 | Frontend | Improved error messages with custom text for specific sign-in error codes. | Auth
2026-06-18 | Frontend | Replaced the document history drawer with a version-history popup and made it refresh after a restore. | Editor
2026-06-18 | Frontend | Added file-size validation and improved the page-number renumbering logic. | Editor
2026-06-18 | Frontend | Added a duplicate filename check for cloud uploads and improved upload handling. | File Handling
2026-06-18 | Frontend | Improved sign-in via Google callback handling, renamed My files to My PDFs, tidied version history, added a signature tool, and handled document-load errors with a friendly dashboard redirect. | Auth
2026-06-18 | Frontend | Added automatic page-number renumbering after page operations and improved dimension controls on mobile. | Editor
2026-06-17 | Frontend | Added a fallback for special characters that can't be encoded when drawing text. | Editor
2026-06-17 | Frontend | Improved editor route handling for document ID validation and user redirects. | Editor
2026-06-17 | Frontend | Simplified how source text is handled during the PDF merging process. | Editor
2026-06-17 | Frontend | Improved text encoding when drawing edited text runs. | Editor
2026-06-17 | Frontend | Improved handling and saving of edit-mode text. | Editor
2026-06-17 | Frontend | Improved PDF export to correctly include text and shape edits. | Editor
2026-06-17 | Frontend | Added a delete button to the floating text toolbar and improved page-number format labels. | Editor
2026-06-17 | Frontend | Improved the positioning and styling of the floating text toolbar. | Editor
2026-06-17 | Frontend | Minor internal update. | DevOps / Infra
2026-06-17 | Frontend | Minor internal update. | DevOps / Infra
2026-06-17 | Frontend | Refactored the PDF editor tests and updated export functionality. | Testing
2026-06-17 | Backend | Updated versioning to snapshot the pre-save state for more reliable rollback. | Editor
2026-06-16 | Frontend | Minor internal update. | DevOps / Infra
2026-06-16 | Frontend | Added a controlled mobile drawer in the site navbar and required sign-in for loading documents. | Auth
2026-06-16 | Frontend | Improved page-number addition with live on-canvas overlays. | Editor
2026-06-16 | Frontend | Added a background colour picker for page backgrounds. | Editor
2026-06-16 | Frontend | Added an Annotations popup and hooked it into the hamburger menu and editor shell. | Editor
2026-06-16 | Frontend | Refined the PDF merging logic to better handle user edits and improve text rendering. | Editor
2026-06-16 | Frontend | Improved text editing and version-preview functionality. | Editor
2026-06-16 | Backend | Added upsert and cloud-upsert methods for document handling. | File Handling
2026-06-15 | Frontend | Reverted to sending the original file when extracting images to avoid flattening text. | Editor
2026-06-15 | Frontend | Removed the form-fields feature from the hamburger menu. | Editor
2026-06-15 | Frontend | Passed the auth token to the viewer for password-protected share links. | Auth
2026-06-15 | Frontend | Made the app save before extracting images to prevent canvas corruption. | Editor
2026-06-15 | Frontend | Implemented the frontend contract for public share links. | File Handling
2026-06-15 | Frontend | Added an in-memory store for share-token metadata claims. | Auth
2026-06-15 | Frontend | Added a show/hide password toggle in the password gate and share popup. | Auth
2026-06-15 | Frontend | Added version history with restore capability, including a new version-history popup. | Editor
2026-06-15 | Backend | Added document versioning with restore and listing capabilities. | Editor
2026-06-15 | Backend | Added the ability to share PDF files. | File Handling
2026-06-14 | Frontend | Added an Edit Text tool and refactored how text editing works on mobile. | Editor
2026-06-14 | Frontend | Improved error handling and visibility for unsupported text editing on some mobile browsers. | Editor
2026-06-14 | Frontend | Added a compatibility patch so Edit Text works on iOS Safari. | Editor
2026-06-14 | Frontend | Added an opt-in mobile text-editing feature with a fallback for older browsers. | Editor
2026-06-13 | Frontend | Added form fields and page-numbering functionality to the editor. | Editor
2026-06-12 | Backend | Improved cross-site access configuration to support dynamic origins in non-production environments. | DevOps / Infra
2026-06-10 | Frontend | Updated support email references from the old domain to pdfedits.io across the app. | UI / UX
2026-06-10 | Frontend | Updated internal off-limits guidelines to reflect recent user-approved changes. | DevOps / Infra
2026-06-10 | Frontend | Improved popover alignment. | UI / UX
2026-06-10 | Frontend | Improved popover alignment and refactored the Manage Pages popup state management. | UI / UX
2026-06-10 | Frontend | Switched to a legacy PDF library build for compatibility with older iOS Safari. | Editor
2026-06-10 | Frontend | Refactored image extraction to use the live canvas so user-added images are included in the PDF. | Editor
2026-06-10 | Frontend | Improved the PDF viewer layout on mobile with better scrolling and centring. | UI / UX
2026-06-10 | Frontend | Added a legacy PDF build with compatibility patches for older iOS Safari. | Editor
2026-06-10 | Frontend | Improved touch handling for drawing tools on the editor canvas. | Editor
2026-06-10 | Frontend | Improved touch scrolling in the editor canvas for a better experience on iOS Safari. | Editor
2026-06-10 | Frontend | Improved error handling in text extraction to better tolerate malformed PDFs. | Editor
2026-06-10 | Frontend | Improved sign-in popup handling and error messaging for the Google Drive picker. | Auth
2026-06-10 | Backend | Added additional allowed domains for cross-site access. | DevOps / Infra
2026-06-10 | Backend | Improved cross-site access configuration to support dynamic origins in non-production environments. | DevOps / Infra
2026-06-09 | Frontend | Updated references from PDFedits to Content Clicks LLC across the app. | UI / UX
2026-06-09 | Frontend | Fixed unsaved changes and stale-upload issues in the editor flow. | Editor
2026-06-09 | Frontend | Adjusted column sizes and headers for a better documents-table layout. | Dashboard
2026-06-09 | Frontend | Added auto-save before opening Manage Pages and improved save handling in the editor. | Editor
2026-06-09 | Frontend | Added support for more file formats in PDF conversion. | File Conversion
2026-06-09 | Frontend | Added a live preview for replaced text in the Find & Replace popup. | Editor
2026-06-09 | Backend | Added paginated user listing with search for the admin panel. | Dashboard
2026-06-09 | Backend | Added user activation and role management features with admin controls. | Auth
2026-06-09 | Backend | Added support for bundling multi-page PDF exports as a ZIP file, with a proper download filename header. | File Handling
2026-06-09 | Backend | Added support for more input formats and their file signatures during conversion. | File Conversion
2026-06-09 | Backend | Added a fallback admin email for demo deployments in the Clerk authentication strategy. | Auth
2026-06-09 | Backend | Added per-environment configuration for allowed cross-site origins. | DevOps / Infra
2026-06-09 | Backend | Added an allow-list environment variable for promoting users to admin. | Auth
2026-06-08 | Frontend | Updated internal upload options type and temporarily hid the Google Drive upload option. | File Handling
2026-06-08 | Frontend | Temporarily hid the device upload option in the cloud upload row. | File Handling
2026-06-08 | Frontend | Added duplicate file upload handling in the editor. | File Handling
2026-06-08 | Frontend | Added a show/hide password toggle and a user-sync feature. | Auth
2026-06-08 | Frontend | Refactored code for readability and maintainability. | DevOps / Infra
2026-06-08 | Backend | Added a Clerk JWT verification strategy with comprehensive tests and audit logging. | Auth
2026-06-08 | Backend | Improved PDF-to-XLS and PDF-to-XLSX conversion with intermediate-format support. | File Conversion
2026-06-08 | Backend | Improved PDF conversion capabilities across all conversion adapters. | File Conversion
2026-06-07 | Frontend | Improved mobile text rendering by adjusting the text-suppression setting. | Editor
2026-06-07 | Frontend | Added image format validation and improved save-flow management in the editor. | Editor
2026-06-07 | Frontend | Added a new PDF editing page layout and components. | Editor
2026-06-07 | Frontend | Made fonts finish loading before rendering text in edit mode and on the canvas. | Editor
2026-06-07 | Frontend | Improved the mobile experience by adding a fit-to-width option in the viewer. | UI / UX
2026-06-07 | Backend | Improved PDF encryption to support AES-128 and AES-256 with better argument handling. | Editor
2026-06-07 | Backend | Added an option to treat warnings as non-fatal during PDF encryption and decryption. | Editor
2026-06-07 | Backend | Finished the security audit. | DevOps / Infra
2026-06-05 | Frontend | Added Find and Replace functionality with a popup for searching and replacing text in PDFs. | Editor
2026-06-05 | Frontend | Improved editor state management, added watermark and background-image configs, added editor rehydration, and optimised uploads. | Editor
2026-06-05 | Frontend | Added password protection with a popup for encrypting and decrypting PDFs. | Editor
2026-06-05 | Backend | Fixed the fallback logic for the database connection string in the Prisma config. | DevOps / Infra
2026-06-05 | Backend | Updated the encryption key length to use RC4-128 in the tests. | Testing
2026-06-05 | Backend | Updated the Dockerfile to include the Prisma config and adjusted the startup command for migrations. | DevOps / Infra
2026-06-05 | Backend | Adjusted the database connection string during Docker build to use a placeholder. | DevOps / Infra
2026-06-05 | Backend | Refactored the database connection string handling in the Prisma config for clarity. | DevOps / Infra
2026-06-05 | Backend | Added editor-state support for document uploads and updates. | Editor
2026-06-05 | Backend | Added PDF encryption, decryption, flattening, and image-extraction services. | Editor
2026-06-04 | Frontend | Improved image upload validation for the watermark and background-image tools with error handling for unsupported formats and file size limits. | Editor
2026-06-04 | Frontend | Improved editor persistence and navigation with unsaved-changes handling and better user feedback on save. | Editor
2026-06-04 | Frontend | Added a PDF compression feature with a compress popup. | Editor
2026-06-04 | Backend | Added PDF compression tools using Ghostscript. | Editor
2026-06-03 | Frontend | Updated UI behaviour. | UI / UX
2026-06-03 | Frontend | Refactored watermark positioning and scaling with simpler options and better canvas handling. | Editor
2026-06-03 | Frontend | Refactored the smoke test script for HTTP status code checking, removed an outdated test report, and increased worker count. | Testing
2026-06-03 | Frontend | Improved PDF upload and conversion, added undo/redo, and improved various UI elements. | Editor
2026-06-03 | Backend | Improved error handling and cleanup in the file-response interceptor. | DevOps / Infra
2026-06-03 | Backend | Ensured the database connection string is always set in the datasource configuration. | DevOps / Infra
2026-06-03 | Backend | Added a Docker file. | DevOps / Infra
2026-05-25 | Frontend | Completed the W-9 form. | DevOps / Infra
2026-05-25 | Frontend | Added test cases. | Testing
2026-05-25 | Backend | Completed the W-9 form. | DevOps / Infra
2026-05-25 | Backend | Added the event-audit feature. | DevOps / Infra
2026-05-24 | Frontend | Minor internal update. | DevOps / Infra
2026-05-24 | Backend | Added all the file conversions. | File Conversion
2026-05-22 | Frontend | Fixed a page-rotation issue. | Editor
2026-05-22 | Frontend | Fixed a document rotation issue. | Editor
2026-05-22 | Frontend | Progressed work on file conversion. | File Conversion
2026-05-22 | Backend | Progressed work on the tools. | Editor
2026-05-21 | Frontend | Reverted a recent change. | DevOps / Infra
2026-05-21 | Frontend | Fixed a zoom-in/out issue on the Manage Pages feature. | Editor
2026-05-21 | Frontend | Fixed a font issue. | Editor
2026-05-21 | Frontend | Made some performance improvements. | Editor
2026-05-20 | Frontend | Resolved deployment issues. | DevOps / Infra
2026-05-20 | Frontend | Made background colour changes instant and made the colour palette mobile-responsive. | Editor
2026-05-20 | Frontend | Fixed the zoom-in/out issue. | Editor
2026-05-20 | Frontend | Fixed the footer icons and improved the overall footer experience. | UI / UX
2026-05-20 | Frontend | Fixed a build issue. | DevOps / Infra
2026-05-20 | Frontend | Updated watermark properties and functionality. | Editor
2026-05-20 | Frontend | Added the background image feature. | Editor
2026-05-20 | Frontend | Added the background colour feature. | Editor
2026-05-19 | Frontend | Improved watermark handling with layer-order controls and a rotation fix. | Editor
2026-05-19 | Frontend | Added a watermark tool with live preview and PDF export, supporting text and image watermarks with tiled repeat, layer control, opacity, rotation, positioning, and page-scope options; also made the right sidebar context-aware per active tool. | Editor
2026-05-17 | Frontend | Resolved a PDF-save issue after using Manage Pages. | Editor
2026-05-17 | Frontend | Removed redundant width normalisation for text objects on the canvas. | Editor
2026-05-17 | Frontend | Finished the Manage Pages feature. | Editor
2026-05-17 | Frontend | Added the resize-page feature. | Editor
2026-05-15 | Frontend | Removed debug logging and streamlined the text-colour extraction. | Editor
2026-05-15 | Frontend | Added font extraction and embedding to the PDF export pipeline. | Editor
2026-05-15 | Frontend | Improved PDF text-width handling for accurate export spacing. | Editor
2026-05-15 | Backend | Integrated the CloudConvert API for file conversion. | File Conversion
2026-05-14 | Frontend | Finished the Save button work. | Editor
2026-05-13 | Frontend | Improved text editing and extraction capabilities in the editor. | Editor
2026-05-13 | Frontend | Reverted an earlier text-editing implementation. | Editor
2026-05-12 | Frontend | Fixed landing page footer and policy page issues. | UI / UX
2026-05-12 | Frontend | Fixed the footer and removed unnecessary changes. | UI / UX
2026-05-12 | Frontend | Fixed a footer issue. | UI / UX
2026-05-12 | Frontend | Fixed a browser DOM measurement issue by forcing dynamic rendering. | Editor
2026-05-11 | Frontend | Increased default font size and added character-spacing controls for text objects. | Editor
2026-05-11 | Frontend | Added a text-editing mode and text extraction to the editor. | Editor
2026-05-10 | Frontend | Added text extraction and editing tools with better PDF text handling. | Editor
2026-05-09 | Frontend | Updated the font family to Helvetica, improved the signature popup, and improved PDF merging. | Editor
2026-05-09 | Backend | Made the cancellation signal optional in the upsert method and adjusted the call site. | DevOps / Infra
2026-05-09 | Backend | Added a thumbnail generation feature using a background job queue. | Editor
2026-05-07 | Frontend | Updated the overall landing page UI. | UI / UX
2026-05-07 | Frontend | Refactored the code. | DevOps / Infra
2026-05-07 | Frontend | Fixed the deployment workflows. | DevOps / Infra
2026-05-07 | Frontend | Added a Rive-powered animated icon. | UI / UX
2026-05-07 | Frontend | Added multi-select download and bulk delete on the dashboard. | Dashboard
2026-05-07 | Backend | Created the bulk delete documents API. | Dashboard
2026-05-06 | Frontend | Updated the whole UI. | UI / UX
2026-05-06 | Frontend | Pushed an example file. | DevOps / Infra
2026-05-06 | Frontend | Added a Create PDF popup with customisable options. | Editor
2026-05-06 | Frontend | Added an export feature with a PDF download option. | Editor
2026-05-06 | Frontend | Added social-account file upload. | File Handling
2026-05-06 | Frontend | Added the legal pages. | UI / UX
2026-05-06 | Frontend | Added the Bun lock file. | DevOps / Infra
2026-05-06 | Backend | Removed an unwanted env file. | DevOps / Infra
2026-05-06 | Backend | Added the Google Cloud file sync. | File Handling
2026-05-06 | Backend | Added an env example file. | DevOps / Infra
2026-05-01 | Frontend | Made the website responsive for mobile and tablet and updated the logo. | UI / UX
2026-04-30 | Frontend | Updated PDF editor components for better loading states and UI consistency. | Editor
2026-04-30 | Frontend | Added an upload toast system with progress tracking and state management. | File Handling
2026-04-30 | Frontend | Removed unused illustrations for successful uploads, uploading files, and upload errors. | UI / UX
2026-04-30 | Frontend | Refactored code for readability and maintainability. | DevOps / Infra
2026-04-28 | Frontend | Added account settings and preferences management. | Dashboard
2026-04-28 | Frontend | Improved the right sidebar layout and styling for better usability. | UI / UX
2026-04-28 | Frontend | Added customisable styles and link management to the shape tools. | Editor
2026-04-28 | Frontend | Added the PDF.js worker source URL for PDF processing. | Editor
2026-04-28 | Frontend | Added a Bun engine requirement to the package config. | DevOps / Infra
2026-04-28 | Backend | Added upload progress tracking for document uploads. | File Handling
2026-04-27 | Frontend | Updated document handling to use 'filename' instead of 'name'. | Editor
2026-04-27 | Frontend | Added a document management dashboard with upload, rename, and delete. | Dashboard
2026-04-27 | Frontend | Added the dashboard layout and routing. | Dashboard
2026-04-27 | Backend | Reordered cross-site access setup and application startup logic for clarity. | DevOps / Infra
2026-04-27 | Backend | Updated the health-check endpoint and enabled cross-site access for the frontend. | DevOps / Infra
2026-04-25 | Frontend | Added a site footer and enhanced the home page with conversion and feature cards. | UI / UX
2026-04-25 | Frontend | Added highlight and whiteout tools to the editor. | Editor
2026-04-24 | Frontend | Made shape stroke widths stay uniform on non-uniform scaling and improved ellipse scaling and selection behaviour. | Editor
2026-04-24 | Frontend | Added signature and image tools, fixed undo/redo, and refactored the toolbar. | Editor
2026-04-24 | Backend | Added a CLI script for user signup and signin with JWT token generation. | Auth
2026-04-23 | Frontend | Added text-editing tools and history management to the editor. | Editor
2026-04-23 | Frontend | Added shape drawing tools and a shape picker dropdown. | Editor
2026-04-23 | Backend | Updated the script and Prisma config file. | DevOps / Infra
2026-04-23 | Backend | Improved document upload to support upsert. | File Handling
2026-04-23 | Backend | Added the documents module with repository and service. | File Handling
2026-04-23 | Backend | Added JWT authentication to the documents and user controllers. | Auth
2026-04-22 | Frontend | Added the initial PDF editor with core functionality. | Editor
2026-04-21 | Frontend | Refactored auth by extracting logic into hooks, fixed sign-in error routing, and used toasts for server errors. | Auth
2026-04-20 | Frontend | Enhanced the authentication flow with Clerk integration and modularised schema definitions. | Auth
2026-04-20 | Frontend | Added Google sign-in and sign-up, plus a reusable file upload widget. | Auth
2026-04-19 | Frontend | Initial commit. | DevOps / Infra
2026-04-19 | Frontend | Added the sign-in and sign-up flows with Clerk integration. | Auth

## Change Requests - Mobile
PDFVault — Change Requests Since Landing-Page Redesign (30 Jun 2026)
Redesign Inception: 30 Jun 2026 ¦ Report Date: 21 Jul 2026 ¦ Timespan: ~3 Weeks ¦ Total Changes: 194 (FE: 150 · BE: 44)
Redesign Start | Report Date | Calendar Days | Total Changes | FE / BE Split
30 Jun 2026 | 21 Jul 2026 | 22 Days (~3 Weeks) | 194 | 150 Frontend · 44 Backend
SECTION 1 — Mobile Responsiveness (Extra Scope — Not Part of Original Brief)
All rows below are dedicated mobile / tablet / iOS Safari / Android work that landed outside the original brief.
Date | Area | Change Description | Scope Note | Category
2026-05-01 | Frontend | Made the whole website responsive across mobile and tablet, plus logo update. Introduced the mobile detection helper and the bottom dock used for mobile editing. | Extra Scope | Mobile / Responsive
2026-05-20 | Frontend | Added the mobile-friendly color palette and introduced the mobile tool-properties popup so watermark and background-image tools work on small screens. | Extra Scope | Mobile / Responsive
2026-06-07 | Frontend | Added the new mobile-first PDF editing page layout and components. | Extra Scope | Mobile / Responsive
2026-06-07 | Frontend | Added a fit-to-width mode in the mobile PDF viewer so the whole page scales to the screen. | Extra Scope | Mobile / Responsive
2026-06-07 | Frontend | Fixed mobile text rendering so pages aren't blank on iOS Safari (adjusted the pdf.js text-suppression setting). | Extra Scope | Mobile / Responsive
2026-06-10 | Frontend | Improved the PDF viewer layout on mobile by adjusting the scroll container and centering behaviour. | Extra Scope | Mobile / Responsive
2026-06-10 | Frontend | Improved touch-action handling for the drawing tools on mobile. | Extra Scope | Mobile / Responsive
2026-06-10 | Frontend | Switched to the legacy pdf.js build to keep older iOS Safari compatible. | Extra Scope | Mobile / Responsive
2026-06-10 | Frontend | Added iOS Safari polyfills alongside the legacy pdf.js build for compatibility. | Extra Scope | Mobile / Responsive
2026-06-10 | Frontend | Improved touch-scrolling behaviour so zoomed-in pages can be panned smoothly on iOS Safari. | Extra Scope | Mobile / Responsive
2026-06-14 | Frontend | Added a mobile text-editing opt-in with a graceful fallback when the browser can't support it. | Extra Scope | Mobile / Responsive
2026-06-14 | Frontend | Added a polyfill for async streams so Edit Text works on older iOS Safari. | Extra Scope | Mobile / Responsive
2026-06-14 | Frontend | Improved error handling and messaging when text editing isn't supported in a mobile browser. | Extra Scope | Mobile / Responsive
2026-06-14 | Frontend | Made Edit Text its own toolbar tool and reworked how mobile text editing behaves. | Extra Scope | Mobile / Responsive
2026-06-16 | Frontend | Rebuilt the mobile navigation drawer in the site navbar for a cleaner open/close behaviour. | Extra Scope | Mobile / Responsive
2026-06-18 | Frontend | Made the manage-pages dimension-field controls comfortable on small screens. | Extra Scope | Mobile / Responsive
2026-07-10 | Frontend | Added a dedicated mobile Chromium test suite so we catch regressions on smaller viewports automatically. | Extra Scope | Mobile / Responsive
2026-07-16 | Frontend | Switched to a full-page navigation after sign-in so the session sticks reliably on mobile Safari. | Extra Scope | Mobile / Responsive
TOTAL MOBILE CHANGES |  | 18 changes (extra scope)

## Change Requests - Web
SECTION 2 — Full Change Log Since Redesign (30 Jun 2026 → 21 Jul 2026) ¦ 194 Changes
Date | Area | Change Description | Scope | Category
2026-07-21 | Frontend | Added a retry option after a card decline and made sure subscription checks are confirmed before showing the paywall. | Within Scope | Payments & Subscriptions
2026-07-21 | Frontend | Fixed signature centering, toolbar overflow, and improved the layout on convert pages. | Within Scope | File Conversion
2026-07-21 | Frontend | Fixed the home navigation, added a document picker to tool tiles, and made the language dropdown open upward on the dashboard. | Within Scope | Internationalisation
2026-07-21 | Frontend | Fixed the composer so it clears the previous PDF when a user picks a different tool. | Within Scope | Editor
2026-07-21 | Frontend | Confirmed subscription status on the server and stopped an unwanted resync after a user cancels. | Within Scope | Payments & Subscriptions
2026-07-21 | Frontend | Improved the translation service so it loads more efficiently and remembers each user's chosen language. | Within Scope | Internationalisation
2026-07-21 | Frontend | Improved the translation service by saving language choice in the browser and rescanning pages for new content. | Within Scope | Internationalisation
2026-07-21 | Frontend | Aligned the file conversion flow with the client's spec and added a testing harness for user acceptance. | Within Scope | File Conversion
2026-07-21 | Frontend | Added extra diagnostic logging to help track down issues in various components. | Within Scope | DevOps / Infra
2026-07-21 | Frontend | Added the ability to remember a user's chosen language between visits. | Within Scope | Internationalisation
2026-07-20 | Frontend | Removed the Apple sign-in option, tidied the language menu, and added sign-in and paywall checks to the compress tool. | Within Scope | Payments & Subscriptions
2026-07-20 | Frontend | Added a helper that keeps the translated page in sync when users navigate between routes. | Within Scope | Internationalisation
2026-07-20 | Frontend | Replaced the landing page hero illustration with a nicer image. | Within Scope | UI / UX
2026-07-20 | Frontend | Added the ability to automatically resume a file upload after a user signs in, with better handling of files waiting to be processed. | Within Scope | File Handling
2026-07-20 | Frontend | Updated the default theme settings and added a light/dark theme toggle. | Within Scope | UI / UX
2026-07-20 | Frontend | Added dark-mode styling to the landing page and made the theme toggle more visible. | Within Scope | UI / UX
2026-07-20 | Frontend | Added a file preview inside the paywall popup so users can see what they're about to unlock. | Within Scope | Payments & Subscriptions
2026-07-20 | Frontend | Made sure users are signed in and subscribed before exporting or extracting images. | Within Scope | Auth
2026-07-19 | Frontend | Made every signed-out prompt in the editor use the same sign-in popup for consistency. | Within Scope | Auth
2026-07-19 | Frontend | Added a diagnostic trace file to help investigate PDF exports on rotated pages in Chromium. | Within Scope | File Handling
2026-07-18 | Frontend | Added an automated end-to-end test for the signed-out export sign-in flow. | Within Scope | Auth
2026-07-18 | Frontend | Fixed the paywall so signed-out users are sent to sign in first, with a clear escape route if something goes wrong. | Within Scope | Payments & Subscriptions
2026-07-18 | Frontend | Fixed the paywall popup so it no longer appears transparent. | Within Scope | Payments & Subscriptions
2026-07-18 | Frontend | Fixed a race condition that could cancel a successful payment right after it went through. | Within Scope | Payments & Subscriptions
2026-07-18 | Frontend | Fixed the language switcher so it shows every available language, not just English and Spanish. | Within Scope | Internationalisation
2026-07-18 | Frontend | Disabled the translation service's default floating language switcher so only our custom one is visible. | Within Scope | Internationalisation
2026-07-18 | Frontend | Added a CSS-based fallback to hide the translation service's floating switcher when its own setting is ignored. | Within Scope | Internationalisation
2026-07-18 | Frontend | Fixed export so signed-out users are asked to sign in before hitting the paywall. | Within Scope | Payments & Subscriptions
2026-07-18 | Frontend | Made the paywall show up before heavy processing starts, and made cancelling stop it cleanly. | Within Scope | Payments & Subscriptions
2026-07-18 | Frontend | Fixed export so it waits for the sign-in check to complete before running. | Within Scope | Auth
2026-07-18 | Frontend | Removed a brief flash of the drop zone and added a proper confirm dialog for sign-in prompts. | Within Scope | Auth
2026-07-18 | Frontend | Made the All Tools popup close after picking a tile, plus a small batch of editor polish fixes. | Within Scope | UI / UX
2026-07-18 | Frontend | Fixed post-signin restore so files are saved first, then opened, with a loader shown while it happens. | Within Scope | File Handling
2026-07-18 | Frontend | Made uploaded files open through the composer with the correct saved document link. | Within Scope | File Handling
2026-07-18 | Frontend | Added a loading skeleton and a bottom-left upload progress indicator during post-signin restore. | Within Scope | File Handling
2026-07-18 | Frontend | Fixed an issue where the URL was being changed mid-flow during auto-launch, which could break navigation. | Within Scope | Editor
2026-07-18 | Frontend | Stopped sending users back to the dashboard when a document fails to load but they still have a local file open. | Within Scope | Dashboard
2026-07-18 | Frontend | Made the convert flow save signed-in users' files to My PDFs before opening the editor. | Within Scope | Auth
2026-07-18 | Frontend | Added a sign-in requirement to the convert pages for signed-out users. | Within Scope | Auth
2026-07-18 | Frontend | Fixed a build issue by reverting the All Tools catalog to a server component and closing the modal on route change. | Within Scope | DevOps / Infra
2026-07-18 | Frontend | Fixed a build issue by marking the All Tools catalog as a client component so its callbacks work. | Within Scope | DevOps / Infra
2026-07-18 | Frontend | Rebuilt the paywall popup as a clean three-step flow matching the payment design mockup. | Within Scope | Payments & Subscriptions
2026-07-18 | Frontend | Added multi-language SEO tags and expanded the list of translated languages. | Within Scope | Internationalisation
2026-07-18 | Frontend | Added an animated loader and an apologetic message on the editor loading screen. | Within Scope | Editor
2026-07-18 | Frontend | Added bulk delete, a duplicate-name check, the language switcher on all dashboard screens, and improved the document authentication flow. | Within Scope | Auth
2026-07-18 | Backend | Adjusted internal configuration so the translation service key is recognised. | Within Scope | Internationalisation
2026-07-17 | Frontend | Ran a production-readiness audit and shipped critical fixes plus polish improvements. | Within Scope | Editor
2026-07-17 | Frontend | Made every tool tile route through the composer and automatically open the matching dialog. | Within Scope | Editor
2026-07-17 | Frontend | Added support for two-factor sign-in with email, phone, and authenticator app codes. | Within Scope | Auth
2026-07-17 | Frontend | Re-styled the paywall popup with our design tokens and added a data retention notice. | Within Scope | Payments & Subscriptions
2026-07-17 | Frontend | Restyled the cancellation flow to match the paywall design and added a retention notice. | Within Scope | Payments & Subscriptions
2026-07-16 | Frontend | Centered the All Tools popup in the viewport. | Within Scope | UI / UX
2026-07-16 | Frontend | Switched to a full-page navigation after sign-in so the session sticks on mobile Safari. | Within Scope | Auth
2026-07-16 | Frontend | Added pending file storage and hydration so users pick up right where they left off after signing in. | Within Scope | File Handling
2026-07-16 | Frontend | Opened All Tools in a modal and made the landing page auto-save the uploaded file after sign-in. | Within Scope | Auth
2026-07-16 | Frontend | Removed landing page tiles for tools we don't currently offer. | Within Scope | UI / UX
2026-07-16 | Backend | Fixed a strict-typing issue in the billing order-count callback so it compiles cleanly. | Within Scope | Payments & Subscriptions
2026-07-16 | Backend | Finalised the Solidgate payment integration and added a contact form endpoint. | Within Scope | Payments & Subscriptions
2026-07-15 | Frontend | Cleaned up error handling for better readability. | Within Scope | Editor
2026-07-15 | Frontend | Updated the footer contact email to support@pdfvault.ai. | Within Scope | UI / UX
2026-07-15 | Frontend | Fixed the dashboard sidebar logo and expanded how notification toasts are stacked. | Within Scope | Dashboard
2026-07-15 | Frontend | Made the subscription page refresh immediately after closing a subscription so the UI updates instantly. | Within Scope | Payments & Subscriptions
2026-07-15 | Frontend | Added new About Us, FAQs, Onboarding Flow, Subscription Terms, and Refund Policy pages. | Within Scope | Payments & Subscriptions
2026-07-15 | Frontend | Improved the billing settings experience with a warning modal and removed payment-processor branding. | Within Scope | Payments & Subscriptions
2026-07-15 | Frontend | Made the Billing page auto-sync the full payment history on load, plus a manual sync button. | Within Scope | Payments & Subscriptions
2026-07-15 | Frontend | Added a Reset Subscription button so users can self-serve out of stuck states. | Within Scope | Payments & Subscriptions
2026-07-15 | Frontend | Removed old legacy logo and favicon assets in favour of the PDFVault brand marks. | Within Scope | UI / UX
2026-07-15 | Backend | Fixed billing so it uses the correct Solidgate URLs when listing or fetching subscriptions. | Within Scope | Payments & Subscriptions
2026-07-15 | Backend | Stored the cancellation timestamp automatically on cancel so users don't have to manually refresh. | Within Scope | Payments & Subscriptions
2026-07-15 | Backend | Made the billing history show every payment attempt, not just approved ones. | Within Scope | Payments & Subscriptions
2026-07-15 | Backend | Preserved billing history on hard cancellations and cleaned up phantom subscription records. | Within Scope | Payments & Subscriptions
2026-07-15 | Backend | Fixed the parsing of Solidgate's subscription-list response, which returns data as a keyed map. | Within Scope | Payments & Subscriptions
2026-07-15 | Backend | Fixed invoices getting stuck as pending and hid those pending invoices from the invoice list. | Within Scope | Payments & Subscriptions
2026-07-15 | Backend | Made cancel and restore call the correct Solidgate endpoints with valid response codes. | Within Scope | Payments & Subscriptions
2026-07-15 | Backend | Added full self-serve subscription management for users. | Within Scope | Payments & Subscriptions
2026-07-15 | Backend | Added deep history sync from Solidgate exposed via a new endpoint. | Within Scope | Payments & Subscriptions
2026-07-15 | Backend | Added verbose logging on Solidgate REST calls and the history sync for easier debugging. | Within Scope | Payments & Subscriptions
2026-07-15 | Backend | Added logging of the raw Solidgate subscription response and normalised invoice shapes. | Within Scope | Payments & Subscriptions
2026-07-14 | Frontend | Fixed footer legal links, sign-up copy, favicon, Google logo, and dark-mode variants. | Within Scope | Auth
2026-07-14 | Frontend | Showed the restore-subscription confirmation message and handled the closed subscription state better. | Within Scope | Payments & Subscriptions
2026-07-14 | Frontend | Made the top header show a Dashboard button when the user is signed in. | Within Scope | Auth
2026-07-14 | Backend | Kept pre-v3 database driver behaviour when SSL mode is set to required. | Within Scope | DevOps / Infra
2026-07-14 | Backend | Composed the database connection string from AWS Secrets Manager pieces. | Within Scope | DevOps / Infra
2026-07-14 | Backend | Made restore clean up phantom subscription rows when Solidgate returns a not-found error. | Within Scope | Payments & Subscriptions
2026-07-14 | Backend | Made cancel and restore gracefully handle Solidgate's not-found responses. | Within Scope | Payments & Subscriptions
2026-07-13 | Frontend | Updated the paywall layout with new columns and better error and loading states. | Within Scope | Payments & Subscriptions
2026-07-13 | Frontend | Added end-to-end tests for the billing and paywall functionality. | Within Scope | Payments & Subscriptions
2026-07-13 | Backend | Added subscription sync from Solidgate and handling for identity rebinding. | Within Scope | Payments & Subscriptions
2026-07-13 | Backend | Improved handling of Solidgate webhook payloads and subscription processing. | Within Scope | Payments & Subscriptions
2026-07-12 | Frontend | Prettified the empty-state markup for the invoices table. | Within Scope | Payments & Subscriptions
2026-07-12 | Frontend | Simplified the cancellation flow to a two-step feedback and confirm. | Within Scope | Payments & Subscriptions
2026-07-12 | Frontend | Added a global paywall gate at the network layer, both before and after each request. | Within Scope | Payments & Subscriptions
2026-07-12 | Frontend | Added the invoice history table to the billing page. | Within Scope | Payments & Subscriptions
2026-07-12 | Frontend | Added the cancellation and downsell popup to the billing page. | Within Scope | Payments & Subscriptions
2026-07-12 | Frontend | Added the billing settings tab to the dashboard. | Within Scope | Payments & Subscriptions
2026-07-12 | Frontend | Added the paywall popup and the subscription entitlement hook. | Within Scope | Payments & Subscriptions
2026-07-12 | Frontend | Updated the subscription documentation to reflect our single trial-to-monthly plan. | Within Scope | Payments & Subscriptions
2026-07-12 | Frontend | Added a user-journey walkthrough to the subscription documentation. | Within Scope | Payments & Subscriptions
2026-07-12 | Backend | Added unit tests covering webhook signature verification and idempotency. | Within Scope | Payments & Subscriptions
2026-07-12 | Backend | Removed the standalone annual plan from the catalog. | Within Scope | Editor
2026-07-12 | Backend | Removed the downsell tiers from the cancellation flow. | Within Scope | Payments & Subscriptions
2026-07-12 | Backend | Added the invoice endpoint. | Within Scope | Payments & Subscriptions
2026-07-12 | Backend | Added the lifecycle email pipeline via Amazon SES. | Within Scope | Editor
2026-07-12 | Backend | Added the cancellation feedback and downsell endpoints. | Within Scope | Payments & Subscriptions
2026-07-12 | Backend | Added the cancel and restore subscription endpoints. | Within Scope | Payments & Subscriptions
2026-07-12 | Backend | Added the webhook receiver and the reconciliation queue. | Within Scope | Payments & Subscriptions
2026-07-12 | Backend | Added the checkout intent and entitlement endpoints. | Within Scope | Payments & Subscriptions
2026-07-12 | Backend | Set up the initial billing module skeleton, database schema, and configuration. | Within Scope | Payments & Subscriptions
2026-07-12 | Backend | Added subscription discovery notes and an integration plan document. | Within Scope | Payments & Subscriptions
2026-07-11 | Frontend | Renamed the PDF Editor to PDF Composer everywhere, updating all related routes and links. | Within Scope | Editor
2026-07-10 | Frontend | Forced a fresh deployment of the frontend service. | Within Scope | DevOps / Infra
2026-07-10 | Frontend | Removed an invalid button style that was breaking the thumbnail sidebar. | Within Scope | Dashboard
2026-07-10 | Frontend | Fixed a type issue when converting saved PDF bytes into a downloadable file. | Within Scope | File Conversion
2026-07-10 | Frontend | Added a password show/hide toggle and strength meter, and improved button styles. | Within Scope | UI / UX
2026-07-10 | Frontend | Triggered a redeploy after updating cloud permissions. | Within Scope | File Handling
2026-07-10 | Frontend | Made the frontend build fetch secrets from AWS Secrets Manager and added a local build script. | Within Scope | DevOps / Infra
2026-07-10 | Frontend | Added an automatic secret scan on every push and pull request. | Within Scope | DevOps / Infra
2026-07-10 | Frontend | Removed unused image assets from the landing page. | Within Scope | UI / UX
2026-07-10 | Frontend | Refactored the PDF editor tests for better reliability and coverage. | Within Scope | Testing
2026-07-10 | Backend | Made AWS credentials optional so the container's own role can be used automatically. | Within Scope | DevOps / Infra
2026-07-10 | Backend | Added a health-check endpoint and a five-minute grace period for the container health checks. | Within Scope | DevOps / Infra
2026-07-10 | Backend | Improved Clerk webhook handling with raw-body support for signature verification. | Within Scope | Payments & Subscriptions
2026-07-10 | Backend | Fixed the deployment workflow to use the correct backend service name. | Within Scope | DevOps / Infra
2026-07-10 | Backend | Made the deployment workflow auto-discover the backend service name. | Within Scope | DevOps / Infra
2026-07-10 | Backend | Added an automatic secret scan on every push and pull request. | Within Scope | DevOps / Infra
2026-07-10 | Backend | Added an automatic deployment workflow for the backend. | Within Scope | DevOps / Infra
2026-07-10 | Backend | Added debug logging around Clerk auth and webhook user creation. | Within Scope | Payments & Subscriptions
2026-07-09 | Frontend | Refactored code structure for readability and maintainability. | Within Scope | Editor
2026-07-08 | Frontend | Updated branding from PDFedits.io to pdfvault.ai across the app. | Within Scope | UI / UX
2026-07-08 | Frontend | Renamed authentication routes for consistency. | Within Scope | Auth
2026-07-08 | Frontend | Adjusted the landing header height and updated the logo link. | Within Scope | UI / UX
2026-07-08 | Frontend | Updated authentication routes for consistency. | Within Scope | Auth
2026-07-08 | Frontend | Added better logging for Google Drive picker actions and visibility. | Within Scope | File Handling
2026-07-08 | Frontend | Improved error handling and logging for the Google Drive picker startup. | Within Scope | File Handling
2026-07-08 | Frontend | Added an Open action to the file table so users can jump into the editor from the dashboard. | Within Scope | Dashboard
2026-07-08 | Frontend | Added a pixel-accurate sign-up screen with Google sign-up support. | Within Scope | Auth
2026-07-08 | Frontend | Added new dashboard illustrations for the Sign & Watermark and Word to PDF tools. | Within Scope | Dashboard
2026-07-08 | Frontend | Added dashboard styles and design tokens for the PDFVault look. | Within Scope | Dashboard
2026-07-08 | Frontend | Added the sidebar navigation design asset from Figma. | Within Scope | Dashboard
2026-07-07 | Frontend | Improved how we detect when the sign-in popup closes and removed a polling workaround. | Within Scope | Auth
2026-07-07 | Frontend | Updated the Google sign-in scope so users can pick files from Drive. | Within Scope | Auth
2026-07-07 | Frontend | Fixed the sign-in page so the form starts below the top menu bar. | Within Scope | Auth
2026-07-07 | Frontend | Added a drag-and-drop file upload zone and improved the offline banner. | Within Scope | File Handling
2026-07-07 | Frontend | Added cloud upload options alongside the existing device upload. | Within Scope | File Handling
2026-07-07 | Frontend | Added debug logging for the Google Drive picker and sign-in events. | Within Scope | Auth
2026-07-07 | Frontend | Added the Google Cloud project number needed for Drive Picker file access. | Within Scope | File Handling
2026-07-07 | Frontend | Wired the Login with Google button on the sign-in page into the Clerk flow. | Within Scope | Auth
2026-07-06 | Frontend | Updated all tool links to use the PDF editor route for consistency. | Within Scope | Editor
2026-07-06 | Frontend | Added file conversion functionality and related UI. | Within Scope | File Conversion
2026-07-06 | Frontend | Added Terms and Conditions and improved the legal sections. | Within Scope | Editor
2026-07-06 | Frontend | Added the All Tools page and the policy pages under the landing shell. | Within Scope | Editor
2026-07-06 | Frontend | Added a pixel-accurate sign-in screen. | Within Scope | Auth
2026-07-05 | Frontend | Skipped loading the translation service on the landing page when the API key is missing. | Within Scope | Internationalisation
2026-07-05 | Frontend | Guarded against the translation service being missing when the language switcher loads. | Within Scope | Internationalisation
2026-07-05 | Frontend | Added a sticky header, animated tabs and cards, and a refined footer to the landing page. | Within Scope | UI / UX
2026-07-05 | Frontend | Promoted the new PDFVault landing page to the site's home page. | Within Scope | UI / UX
2026-07-05 | Frontend | Triggered a Railway rebuild. | Within Scope | DevOps / Infra
2026-07-05 | Frontend | Pinned the Railway start command to our standalone server. | Within Scope | DevOps / Infra
2026-07-05 | Frontend | Added a production start script mirroring the Docker command. | Within Scope | DevOps / Infra
2026-07-03 | Frontend | Updated branding from PDFedits.io to PDFVault across the app. | Within Scope | UI / UX
2026-07-03 | Frontend | Fixed the deployment workflow to use the correct frontend service name. | Within Scope | DevOps / Infra
2026-07-03 | Frontend | Fixed the deployment workflow to use the correct frontend service name. | Within Scope | DevOps / Infra
2026-07-03 | Frontend | Added a GitHub Actions workflow for deploying the frontend automatically. | Within Scope | DevOps / Infra
2026-07-03 | Frontend | Added a GitHub Actions workflow for deploying the frontend automatically. | Within Scope | DevOps / Infra
2026-07-03 | Frontend | Added a GitHub Actions workflow for deploying the frontend automatically. | Within Scope | DevOps / Infra
2026-07-03 | Frontend | Scaffolded the subscription surface for Chargebee and Adyen. | Within Scope | Payments & Subscriptions
2026-07-03 | Frontend | Routed subscription checks, checkout, and portal through the backend API. | Within Scope | Payments & Subscriptions
2026-07-03 | Frontend | Added an Adyen webhook endpoint with signature verification. | Within Scope | Payments & Subscriptions
2026-07-03 | Backend | Improved webhook handling by using the raw request body for signature verification. | Within Scope | Payments & Subscriptions
2026-07-03 | Backend | Added the subscription and Adyen/Chargebee webhook infrastructure. | Within Scope | Payments & Subscriptions
2026-07-03 | Backend | Enabled automatic backend deployment on every push to main. | Within Scope | DevOps / Infra
2026-07-02 | Frontend | Set the icon-only PNG as the new landing page favicon. | Within Scope | UI / UX
2026-07-01 | Frontend | Fixed the landing page upload section to match the design. | Within Scope | File Handling
2026-07-01 | Frontend | Updated the footer to use the real vault-contour artwork with a measured grid. | Within Scope | UI / UX
2026-07-01 | Frontend | Added a language switcher to the new landing page. | Within Scope | Internationalisation
2026-06-30 | Frontend | Applied consistent formatting across the landing page sections. | Within Scope | UI / UX
2026-06-30 | Frontend | Added extra breathing space to the hero, upload box, and steps section. | Within Scope | File Handling
2026-06-30 | Frontend | Restored the footer chevron pattern from the original design. | Within Scope | DevOps / Infra
2026-06-30 | Frontend | Updated the footer to use the correct motif from the design art. | Within Scope | UI / UX
2026-06-30 | Frontend | Traced the banner tile layout from the reference art for pixel accuracy. | Within Scope | UI / UX
2026-06-30 | Frontend | Rebuilt the banner gradient and tile pattern to match the design. | Within Scope | UI / UX
2026-06-30 | Frontend | Simplified the footer background to a single centred circle. | Within Scope | DevOps / Infra
2026-06-30 | Frontend | Fixed the footer colour and added a ribbon texture. | Within Scope | UI / UX
2026-06-30 | Frontend | Added Docker support with a Dockerfile and ignore file. | Within Scope | File Handling
2026-06-30 | Frontend | Wired the landing page header buttons to the Clerk sign-in and sign-up routes. | Within Scope | Auth
2026-06-30 | Frontend | Added a new PDFVault landing page with header, hero, upload area, and steps. | Within Scope | File Handling
2026-06-30 | Frontend | Updated the hero background to use the real inverted grid asset. | Within Scope | UI / UX
2026-06-30 | Frontend | Added a scrolling testimonials section to the landing page. | Within Scope | Testing
2026-06-30 | Frontend | Added a red conversion banner section to the landing page. | Within Scope | File Conversion
2026-06-30 | Frontend | Added a deep-maroon footer section to the landing page. | Within Scope | UI / UX
2026-06-30 | Frontend | Added the PDF tools catalog section to the landing page. | Within Scope | UI / UX
2026-06-30 | Frontend | Removed a large unused reference image from the public folder. | Within Scope | Editor
2026-06-30 | Backend | Improved how AWS storage credentials are handled for different deployment environments. | Within Scope | File Handling
2026-06-30 | Backend | Added a dedicated health-check endpoint for our AWS load balancer and containers. | Within Scope | DevOps / Infra
TOTAL CHANGES (WITHIN SCOPE) |  | 194 changes